PROJECT KICKOFF

What We Build First & What It Costs to Start

We start with the part that takes bookings and makes money: the equipment catalog and online booking system. GPS tracking follows in Phase 2, once the platform is live and earning. Stack: Next.js + Node.js + PostgreSQL — modern, low-cost, and scales as the business grows.

1. What we need from the business (week 1)

- Machine list — every machine with make, model, year, key specs, and hourly / daily / weekly rates. Phone photos are fine to start.

- Rental terms — deposit amount, late-return and damage policy, with/without operator, who pays transport and fuel.

- Business documents — business registration certificate and bank account details — required to open the Paystack account that receives online payments.

- One decision-maker — who approves bookings, and who answers questions during the build.

2. Startup budget (cash needed to launch)

| Item | Cost | Notes |
| --- | --- | --- |
| Domain name (.com / .com.gh) | $15–20 / year | One-time yearly |
| Hosting — Vercel free tier | $0 | Upgrade later if needed |
| Database — Neon / Supabase free tier | $0 | Upgrade ~$25/mo at scale |
| Email notifications — free tier | $0 | Resend / similar |
| SMS credits (Arkesel / Hubtel) | ~$10 to load | Pay-as-you-go |
| Paystack account | Free to open | ~1.95% per transaction |
| TOTAL CASH TO LAUNCH | Under $50 | Excludes developer time |

As traffic grows, hosting and database move to roughly $40–50/month combined — not needed on day one. GPS trackers (~$60–150 per machine one-time + a few dollars monthly per SIM) are deferred to Phase 2, so no hardware spending needs approval today.

3. First 8 weeks of building

| Weeks | What gets built | Result |
| --- | --- | --- |
| Weeks 1–2 | Project setup, data model, public equipment catalog with real machines and rates | Company is visible online |
| Weeks 3–4 | Availability calendar and booking request flow | Customers can request rentals |
| Weeks 5–6 | Admin page: view and approve bookings, mark machines under maintenance | Staff manage everything digitally |
| Weeks 7–8 | Paystack payments (MoMo, cards) for deposits + SMS confirmations | LAUNCH — paid bookings live |

4. Marketing & advertising timeline

Social media starts on day one because it is free and builds an audience while the platform is built. Paid advertising starts only at launch — ads before there is a website to book on waste money.

| When | Marketing activity | Cost |
| --- | --- | --- |
| Weeks 1–2 | Create company accounts: Facebook, Instagram, TikTok, LinkedIn, WhatsApp Business, Google Business Profile — reserve the name everywhere | Free |
| Weeks 3–7 | Organic content: machine photos & videos, job-site clips, behind-the-scenes — 2–3 posts per week building an audience before launch | Free |
| Week 8 — LAUNCH | Paid ads begin: Facebook & Instagram campaigns + boosted posts sending customers to the new website | GHS 1,500–3,000 /month |
| Month 3+ | Add Google Ads for searches like “excavator rental Ghana”; scale only the ads that bring actual bookings | Budget grows with results |

All ad accounts are opened in the company's name and funded by the company's own card — advertising spend is the company's budget, managed (not paid) by the systems manager as part of the ongoing role.

5. What comes after launch

Phase 2 adds GPS tracking, geofencing, and engine-hour billing. Phase 3 adds financial controls, reporting, and analytics. Each phase is approved separately — the business only pays for the next step once the previous one is working and earning.